## Sheet1
Iteration #1 | Feature | Feature | Feature | Feature
Date of milestone | 14th December 2016
Features in scope | Gradle "Hello World" Plugin | Gradle Plugin to Scan Docker Image for JAR files.
Features implemented | Gradle "Hello World" Plugin
Features in deficit this Iteration | Gradle Plugin to Scan Docker Image for JAR files.
Iteration Comments & Summary | Installed and setup Gradle + Docker on 2 VM's. Created a Gradle "Hello World" Plugin. Had issues creating Gradle Plugin to Scan Docker Image for JAR files. May not be feasible so instead may move to scan Docker containers instead of images.
Iteration #2
Date of milestone
Features in scope
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #3
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #4
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary