## Slide 1
IBM Confidential
Paul Kenny – X00107570
Accomplishments:
Refactoring image scan code.
Researching NVD access.
Attempting to integrate temporary ram disk creation to speed up scan process.
Upcoming Work:
Add functionality to Gradle plugin.
Cross-reference Docker image jars with NVD.
Possibly create cloud based data base of 3rd party jar information and associated vulnerabilities.
Issues/risks:
No NVD api. NVD supply vulnerability data through in bulk through RSS feed/XML downloads only.
Project Title | Overall Status
Security Vulnerabilities Scan | Green
Milestone | Target Date | Actual Date | Status
Use cases and Tech. Arch Complete | 16/11/16 | 16/11/16 | complete
Iteration 1 Complete | 14/12/16 | 14/12/16 | complete
Iteration 2 Complete | 08/02/17 | 08/02/17 | complete
Iteration 3 Complete | 01/03/17 |  | complete
Iteration 4 Complete | 22/03/17 |  | 
Iteration 5 Complete | 05/04/17 |  | 
Iteration 6 Complete | 26/04/17 |  | 
Project Complete | 03/05/17 |  | 
Notes: 1